## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
Product sales and Analysis
Company name | Big company |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead |  | Liang Guo
Project Start Date: | 2021-10-11 |  |  |  |  | October | [20 empty] | November
Scrolling Increment: | 1 | time axis 2021-10-12 to 2021-12-06
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-10-12 to 2021-12-06
lteration1
lteration planning and meeting | Goal | Yichao Ma | 25% | 2021-10-14 | 3 | 2021-10-14: 2; 2021-10-15: 2; 2021-10-16: 2
Complete stakeholder register | High Risk | Liang Guo | 100% | 2021-10-18 | 4
Design persona | Low Risk | Jiarun Ding | 50% | 2021-10-22 | 7
Review and test persona | Med Risk | Minghao Chen | 25% | 2021-10-30 | 1
Complete progress report | On Track | Yichao Ma | 100% | 2021-11-02 | 5
lteration2
lteration planning and meeting | Goal | Liang Guo | 75% | 2021-11-10 | 10 | 2021-11-10: 2; 2021-11-11: 2; 2021-11-12: 2; 2021-11-13: 2; 2021-11-14: 2; 2021-11-15: 2; 2021-11-16: 2; 2021-11-17: 2; 2021-11-18: 2; 2021-11-19: 2
Complete Gantt chart and resources needs | Med Risk | Yichao Ma | 50% | 2021-11-21 | 5
GitHub boards and Test new changes | Low Risk | Jiarun Ding | 25% | 2021-11-26 | 5
Review and test changes | Milestone | Minghao Chen | 25% | 2021-12-01 | 2 | bar: 2021-12-01 to 2021-12-02
Complete progress report | Med Risk | Liang Guo | 100% | 2021-12-04 | 6
lteration3
lteration planning and meeting | Goal | Jiarun Ding | 100% | 2021-12-11 | 5
Complete risk register | Med Risk | Liang Guo | 25% | 2021-12-17 | 3
Complete Website integration and publish | On Track | Yichao Ma | 25% | 2021-12-21 | 2
Collect user feedback | Low Risk | Minghao Chen | 30% | 2021-12-23 | 3
Complete progress report | On Track | Jiarun Ding | 75% | 2021-12-27 | 4
lteration4
Summary all projects | High Risk | Liang Guo | 100% | 2022-01-01 | 15
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Big company
Project Start Date: | 2021-10-11 |  |  |  |  | October | [20 empty] | November
Scrolling Increment: | 1 | time axis 2021-10-12 to 2021-12-06
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
lteration1
lteration planning and meeting | Goal | Yichao Ma | 25% | 2020-10-14 | 3
Complete stakeholder register | High Risk | Liang Guo | 100% | 2021-10-18 | 4
Design persona | Low Risk | Dingjia Run | 50% | 2021-10-21 | 7
Review and test persona | Med Risk | Minghao Chen | 25% | 2021-10-30 | 1
Complete progress report | On Track | Yichao Ma | 100% | 2021-11-02 | 5
lteration2
lteration planning and meeting | Goal | Liang Guo | 75% | 2021-11-10 | 10 | W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2
Complete Gantt chart and resources needs | Med Risk | Yichao Ma | 50% | 2021-11-21 | 5
GitHub boards and Test new changes | Low Risk | Dingjia Run | 25% | 2021-11-26 | 5
Review and test changes | Milestone | Minghao Chen | 25% | 2021-12-01 | 2 | bar: W to T
Complete progress report | Med Risk | Liang Guo | 100% | 2021-12-04 | 6
lteration3
lteration planning and meeting | Goal | Dingjia Run | 100% | 2021-12-11 | 5
Complete risk register | Med Risk | Liang Guo | 25% | 2021-12-17 | 3
Complete Website integration and publish | On Track | Yichao Ma | 25% | 2021-12-21 | 4
Collect user feedback | Low Risk | Minghao Chen | 30% | 2021-12-23 | 3
Complete progress report | On Track | Dingjia Run | 75% | 2021-12-27 | 4
lteration4
Summary all projects | High Risk | Liang Guo | 100% | 2022-01-01 | 15
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-10-13 |  |  |  |  | October | [13 empty] | November | [34 empty] | December
Scrolling Increment: | 5 | time axis 2021-10-18 to 2021-12-12
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-10-18 to 2021-12-12
TITLE 1
Task 1 | Goal | Name | 25% | 2021-10-13 | 3
Task 2 | Milestone |  |  | 2021-10-18 | 1 | bar: 2021-10-18
Task 3 | Low Risk |  | 50% | 2021-10-10 | 10
Task 4 | Milestone |  |  | 2021-11-02 | 1 | bar: 2021-11-02
Task 5 | Med Risk |  | 10% | 2021-10-19 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-10-19 | 13
Task 2 | On Track |  | 50% | 2021-10-21 | 9
Task 3 | Low Risk |  | 33% | 2021-10-26 | 11
Task 4 | Milestone |  |  | 2021-10-28 | 1 | bar: 2021-10-28
Task 5 |  |  |  | 2021-10-29 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-10-28 | 4
Task 2 | Med Risk |  |  | 2021-10-31 | 14
Task 3 | On Track |  |  | 2021-11-15 | 6
Task 4 | Goal |  |  | 2021-11-19 | 3 | 2021-11-19: 2; 2021-11-20: 2; 2021-11-21: 2
Task 5 | Low Risk |  |  | 2021-10-19 | 19
TITLE 4
Task 1 |  |  |  | 2021-11-22 | 15
Task 2 |  |  |  | 2021-12-06 | 5
Task 3 | Milestone |  |  | 2022-01-17 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one